NCD Process Timeline

Steps 2 & 3

Step 2--Diagnosis

Task						         Person(s)				          Due

Select Survey Participants					Team					         Done

Conduct Survey						Team					         Done

Receive Results						Gordon				         Done

TEAM MEETING—TOLL BOOTH				Colin					         Done

Research Minimum Factor & Report to Colin		Gordon				         Done

Communicate Survey Results to Congregation		Kimberly/Colin/Don			         Done

Arrange Focus Groups					Barbara				   6/29-8/15/11

Conduct Focus Groups					Colin/Barbara/Gordon		          7/16, 7/24, 7/27

(Team Participates)		          7/30, 8/14, 8/17

Present Results to Team					Colin					         8/22/11

Discuss 3-5 Key Issues				Team

Select Participants for Action Plan Workshop

Communicate Prayer Concerns				Fritz					         8/22/11

Communicate Progress to Congregation			Kimberly				         8/28/11

Arrange Action Plan Workshop				Barbara				   8/22-8/29/11

Step 3--Planning

Conduct Action Plan Workshop				Colin, Barbara, Gordon		         9/10/11									Team Participates

Prepare Written Plan						Barbara				         9/30/11

Session Buy-in/Approval					Don/Colin/Fritz			         10/4/11

Present Plan to Team						Barbara/Team		                                10/10/11

Select Work Groups

Update Congregation						Don/Colin/Kimberly			         10/16/11

Communicate Prayer Concerns				Fritz				                     10/16/11

Plan Official Launch						Team				          10/24-11/14/11

Congregational Launch

@ Pie & Praise					Don, Colin, Kimberly			       11/20/11

Step 4 (Implementation) will take place according to Timeline established in the Plan with set evaluation, reporting and celebration dates (Step 5) of approximately every 60 days. Appointment of new Health Team scheduled for May, 2012.  Repeat survey scheduled for June 2012.